## Decision Matrix
VIP Infrastructure Decision Matrix
2026-08-23 · SHA dfb74af3ea4e44491fbee946a44e0e5e0e984bbf
Category | Candidate | Need now? | Recommendation | Reason | Timing
DNS/WAF | Cloudflare | Y | Free DNS now; optional proxy | No live DNS; fastest professional names | DO NOW
DNS alt | Route 53 | With AWS | Matches Terraform | Use when account applied | DO BEFORE FIRST PRODUCTION
Transactional Email | Resend | Y | SMTP into existing EmailProvider | Hours to first reset/invite mail | DO NOW
Email Alternative | AWS SES | Prod AWS | email.tf already written (eu-central-1) | Fewer extra vendors once AWS live | DO BEFORE FIRST PRODUCTION
Containers | Docker | Y | Keep | Images exist | DO NOW
Container Registry | ECR | Staging | Matches Terraform | Digest-pinned deploys | DO BEFORE FIRST PRODUCTION
Registry alt | GHCR | Optional | Fine for bridge | If PaaS first | DO NOW if PaaS
App Hosting | ECS/Fargate | Prod | Recommended destination | Already designed; GCC region | DO BEFORE FIRST PRODUCTION
Lower-cost Hosting | Railway/Render | Optional bridge | Temporary pilot only | Do not throw away Terraform | DO NOW only if AWS delayed
Database | RDS PostgreSQL | Prod | Required | Do not self-host PG in prod | DO BEFORE FIRST PRODUCTION
Cache/Queue | ElastiCache Redis | Prod | Required | Jobs + rate limit | DO BEFORE FIRST PRODUCTION
File Storage | EFS + local driver | Prod | V1 target | No S3 adapter shipped | DO BEFORE FIRST PRODUCTION
File Storage later | S3 | N | Defer adapter | Requires recertify | DEFER
Secrets | AWS Secrets Manager | Prod | In Terraform | No dummy Compose keys | DO BEFORE FIRST PRODUCTION
Secrets alt | Doppler | PaaS bridge | OK on Render | One store | DO NOW if PaaS
Errors | Sentry | Y | Add SDK | Cheap, high leverage | DO BEFORE FIRST PRODUCTION
Uptime | UptimeRobot / Better Stack | Y | External probe | Independent of AWS | DO BEFORE FIRST PRODUCTION
Metrics/Logs | CloudWatch | With AWS | Use IaC | Enough for V1 | DO BEFORE FIRST PRODUCTION
Metrics alt | Grafana stack | N | Defer | Overkill | DEFER
CDN/TLS | Cloudflare or ACM | Y | One real certificate | Never Flexible TLS | DO NOW DNS / P3 ACM
Backups | RDS PITR + AWS Backup + EFS | Prod | Required + restore test | Local drill insufficient | DO BEFORE FIRST PRODUCTION
CI/CD | GitHub Actions | Y | Prove deploy workflow | Files exist; runs NOT VERIFIED | DO BEFORE FIRST PRODUCTION
K8s | EKS | N | Reject | Five processes | DEFER
Observability extra | OTel | N | Defer | Sentry first | DEFER

## Cost Classes
Cost classes (no fabricated bills)
Unsafe cuts listed
Choice | Cost class | Safe to skip now? | Risk if skipped
Cloudflare Free DNS | Very Low | N | No professional URL/email DNS
Resend | Very Low / Low | N | No password reset/invites
Sentry + UptimeRobot | Very Low / Low | N for prod | Silent outage
Render/Railway pilot | Low / Moderate | Y if AWS staging this month | Migration later; weaker GCC story
ECS+RDS+Redis+EFS+ALB single-AZ staging | Moderate | N for real prod | Still a laptop product
Multi-AZ + dual NAT + DR region | High | Y | Wait for revenue/SLA
Cloudflare Enterprise | High | Y | Unnecessary
Kubernetes | High | Y | Complexity without benefit
Skipping backups | False saving | N | Unrecoverable customer data
noop malware scanner in prod | False saving | N | Upload malware
HTTP cookies on public URL | False saving | N | Session theft

## Minimum Product Stack
Minimum stack for a real product
First 1–5 customers, shared tenancy
Layer | Choice | Shared vs dedicated | When
DNS | Cloudflare Free | Shared | Now
Domain | Company-owned | Shared | Now
SSL | Cloudflare Full Strict or ACM | Shared | Now / P3
Frontend | ECS web or PaaS static | Shared | P3
API | ECS API | Shared | P3
Worker | ECS dashboard + pipeline | Shared | P3
Scheduler | ECS desired_count=1 | Shared singleton | P3
PostgreSQL | RDS | Shared instance, tenant in app | P3
Redis | ElastiCache | Shared | P3
Files | EFS | Shared volume, tenant prefixes | P3
Email | Resend then SES | Shared sending domain | P1 then P3
Secrets | Secrets Manager | Shared | P3
Logs | CloudWatch | Shared | P3
Errors | Sentry | Shared project | P3
Uptime | UptimeRobot | Shared monitors | P3
Backups | RDS+EFS | Shared | P3
CI/CD | GitHub Actions | Shared | P2–P3
Staging | Second Terraform env | Shared | P3 required
Production | Third env | Shared until contract requires split | P3
Per-customer cluster | — | Dedicated later | P5 / contract