## Executive Summary
VIP Market Readiness — Executive Summary
2026-08-23 · SHA dfb74af3ea4e44491fbee946a44e0e5e0e984bbf · Application not modified
Commercial verdict | C — PILOT READY ONLY
Item | Value
Overall score | 51 / 100
Application maturity | 74%
SaaS productization | 31%
Demo | READY WITH CONDITIONS
PoC / Pilot | READY WITH CONDITIONS
First paying customer | READY WITH CONDITIONS (pilot SOW)
Production | NOT READY
Enterprise scale | NOT READY
Live AWS apply | NOT VERIFIED / NOT EXECUTED
Docker during audit | DOWN — runtime NOT VERIFIED
Transactional email | FILE OUTBOX / DISABLED
Invitations | NO EMAIL, NO ACCEPT UI
Legal pack | ABSENT
# | Question | Answer
1 | Demo today? | YES WITH CONDITIONS — Compose + PG/CSV script. Docker was down during audit.
2 | Controlled trial? | YES WITH CONDITIONS — operator-provisioned users until invite email.
3 | Sign first paying customer? | YES WITH CONDITIONS — paid pilot SOW, not production SaaS.
4 | Deploy paying customer to production? | NO — Terraform unapplied.
5 | Operate reliably afterward? | NOT YET — paper runbooks only.
6 | Missing infrastructure? | Domain, DNS, TLS, live ECS/RDS/Redis/EFS, email, secrets, Sentry, uptime, backups, staging, legal.
7 | Implement first? | Demo stack → domain/Cloudflare → Resend+invites → legal → AWS staging → backups/monitor → tag → production.
8 | What can wait? | K8s, SOC2, 90 connectors, AI/Reports/Automation/Marketplace/Billing, S3 adapter, multi-region.
9 | Feel like real SaaS? | HTTPS URL, real email, versioned SHA, restored backups, support human, honest limits PDF.
10 | Minimum production stack? | See VIP_INFRASTRUCTURE_DECISION_MATRIX.xlsx / VIP_PRODUCTION_ARCHITECTURE.md

## Findings
Findings register
Independent 23 Aug 2026 tree — no silent fixes
ID | Area | Title | Evidence | Severity | Business impact | Technical impact | Demo blocker? | Pilot blocker? | Sale blocker? | Prod blocker? | Action | Owner | Effort | Dependency | Acceptance criteria | Phase
FIND-001 | Deployment | No live staging or production | Terraform unapplied; Docker down this audit | Critical | Cannot host paying customer | No public control plane | N | Condition | Condition | Y | Apply staging then production | DevOps | L | AWS account, domain | HTTPS smoke + two-tenant isolation | P3
FIND-002 | Email | Transactional email not live | DASHBOARD_EMAIL_PROVIDER file/disabled; production requires smtp | High | Reset/invites fail for real users | No live SMTP | N | Condition | Y self-serve | Y | Resend SMTP now; SES later | Backend | S | Domain DNS | External mailbox receives reset | P1
FIND-003 | Onboarding | Invitations are not a product | No send; token only in dev/test; no accept UI; no public signup | High | Cannot invite a team | Dead INVITATION_ACCEPT_URL | N | Condition | Y if selling invites | Y | Email + accept page + create user | Full stack | M | FIND-002 | Gmail invite joins unassisted | P1
FIND-004 | Commercial | No legal/commercial pack | No Terms/Privacy/DPA/PDPL/SLA/pricing | Critical | Cannot invoice enterprise honestly | Contractual vacuum | N | Y paid pilot | Y | Y | Counsel pack | Legal+Founder | M | Architecture PDF | Signed PDFs | P2
FIND-005 | DNS | Domain placeholder | root_domain=example.com | High | No professional URL | ACM/email blocked | N | Y public trial | Y | Y | Buy domain; Cloudflare DNS | Founder | S | Budget | nslookup app.domain | P1
FIND-006 | Storage | Local filesystem only | local provider only; EFS in Terraform | High | Data loss on ephemeral disk | Uploads not durable on cattle nodes | N | Condition | Y if laptop disk | Y | EFS + backups | DevOps | M | AWS | Replace task; file remains | P3
FIND-007 | Security | Auth rate limit fails open | RedisError returns False | Medium | Brute force if Redis down | Limit bypass | N | N | N | Harden | Fail closed in production | Backend | S | None | Unit test Redis down → 429/503 | P2
FIND-008 | Secrets | Compose dummy keys + worker noop scanner | Dummy encryption key; FILE_MALWARE_SCANNER=noop | High | Unsafe if copied to prod | Decryptable secrets / unscanned uploads | N | Y hosted defaults | Y | Y | Secrets Manager; ClamAV all workers | DevOps | S | FIND-001 | No dummy keys; EICAR blocked | P3
FIND-009 | Product | Connector catalog vs GA depth | ~100 types; GA PG+file; semantic PG-only | Medium | Trust damage if oversold | Preview/semantic reject non-PG | Condition | Condition | N as GA | N as GA | Sales matrix; Available filter | PM+Sales | S | None | Demo uses only GA types | P0
FIND-010 | Release | Release not frozen | 60 commits ahead; 0.1.0; dirty tree | Medium | Unknown running SHA | Unreproducible | N | Y | Y | Y | Tag v0.9.0-pilot; inject SHA | Founder | S | CI green | version shows tag+SHA | P2
FIND-011 | Compliance | Bahrain ≠ KSA residency | me-south-1; SES eu-central-1 | High | SOE deals fail if implied in-country | Cross-border processors | N | Disclose | Y if implied KSA | Y if implied KSA | Written residency letter | Legal | S | FIND-004 | Customer signed disclosure | P2
FIND-012 | Observability | No live error/uptime product | No Sentry; CW unapplied | Medium | Silent failure | No on-call loop | N | Condition | Y prod claims | Y | Sentry + UptimeRobot | DevOps | S | HTTPS URL | Forced 500 alerts | P3
FIND-013 | DR | AWS restore never executed | Local drill PASS; AWS NOT EXECUTED | High | Ceremonial backups | Untested PITR | N | N | Y prod | Y | Restore RDS throwaway | DevOps | M | FIND-001 | API /ready on restored DB | P3
FIND-014 | Release | No staging environment | Required in ops docs; not applied | High | First bug hits customers | No rehearsal | N | Y public trial | Y | Y | Separate staging stack | DevOps | L | FIND-001 FIND-005 | Staging smoke pass | P3
FIND-015 | Jobs | Scheduler topology mismatch | Local ticks in worker; ECS singleton not live | Medium | Duplicate sends if scaled | Double fire | N | N | N | Y | desired_count=1 soak 24h | DevOps | S | FIND-001 | One scheduled delivery | P3
FIND-016 | UX | Favorites hardcoded in mock | developmentMockOnly | Low | Trust if demo in mock | Fake data | Y if mock | N live | N | N | Demo live API only | Founder | XS | None | No Favorites in live nav | P0
FIND-017 | UX | Dashboard templates mock | developmentMockOnly | Low | Fake CTA if shown | Mock | Y if mock | N live | N | N | Keep hidden in live | PM | XS | None | Templates hidden in live | P0
FIND-018 | Security | No MFA / SSO in V1 | Not implemented | Medium | Enterprise questionnaires fail | Password-only | N | N | Condition | Condition | Disclose; do not promise SSO | PM | L later | None | Limitations PDF lists no SSO | P5
FIND-019 | Ops | Handoff docs SHA drift | Docs cite older SHAs; HEAD is dfb74af | Medium | Wrong freeze deployed | Process error | N | Y | Y | Y | Re-pin handoff to tagged SHA | Founder | S | FIND-010 | Handoff SHA == running SHA | P2
FIND-020 | Quality | Tests not re-run this audit | Runtime down | Medium | HEAD quality unknown vs ancestor | Unknown regressions | Condition | Condition | Y | Y | Re-run quality-gate on tag | QA | M | Docker | CI green retries=0 | P2

## Product Modules
Product modules
Gated modules are not V1 failures
Module | Classification | Demo | Trial | Sell | Production | Limitation / evidence
Login / logout / session / lockout / idle | Production Ready (app) | Y | Y | Y | Condition | Needs HTTPS + AUTH_COOKIE_SECURE
Forgot / reset password | Sellable with Limitation | Y | Condition | Condition | N | API+UI exist; email file/disabled
Invitations | Incomplete | Operator | Operator | N self-serve | N | No email, no accept UI, no signup
Org / workspace / RBAC | Production Ready (app) | Y | Y | Y | Condition | Retest isolation on live host
Platform admin user create | Production Ready (app) | Y | Y | Y | Y | must_change_password default true
Connections catalog | Sellable with Limitation | Y | Y | Y honest | Y honest | ~100 types; create blocked if not enabled
PostgreSQL + local_file | Production Ready (app) | Y | Y | Y | Y | GA
MySQL/MSSQL/Snowflake/BQ/S3/REST | Pilot Ready (beta) | Careful | Experimental | N as GA | N as GA | Semantic/preview PG-only
Datasets CSV/XLSX | Production Ready (app) | Y | Y | Y | Y | ClamAV on API; workers noop in Compose
Pipeline Studio | Production Ready (app) | Y | Y | Y | Y | Live REST; 100k row cap
Data Quality | Production Ready (app) | Y | Y | Y | Y | Workspace DQ + pipeline validation
Semantic layer | Sellable with Limitation | Y | Y | Y | Y | PostgreSQL query engine only
Dashboards + publish + viewer | Production Ready (app) | Y | Y | Y | Y | Live
PDF/PNG/CSV/JSON export | Production Ready (app) | Y | Y | Y | Condition | Needs worker + durable storage
Dashboard templates | Intentionally Gated | N live | N | N | N | developmentMockOnly
Favorites | Intentionally Gated | N live | N | N | N | Hardcoded; mock only
Scheduling | Production Ready (app) | Y | Y | Y | Condition | SKIP LOCKED; ECS singleton not live
In-app notifications | Production Ready (app) | Y | Y | Y | Y | Job feed + read state; not email
Settings / Help / Admin | Production Ready (app) | Y | Y | Y | Y | Help is static
Reports / AI / Automation / Billing / Marketplace / Insights / Explore | Intentionally Gated | N | N | N | N | 404 in live; do not sell

## Security
Security
Commercially meaningful controls
Control | Status | Severity if missing live | Evidence | Demo | Pilot | Sale | Prod
Password hashing | In code | Critical | PasswordService | Y | Y | Y | Y
HttpOnly session cookies | In code | High | auth cookies | Y | Y | Y | Y
Secure cookie flag | Fail-closed in production Settings | High | AUTH_COOKIE_SECURE required | N local | Y public HTTP | Y | Y
CSRF | In code | High | origin + double submit | Y | Y | Y | Y
Idle timeout 30m | In code + UI | Medium | useIdleSession | Y | Y | Y | Y
Lockout 5/15 | In code | Medium | auth routes | Y | Y | Y | Y
Refresh rotation | In code | Medium | reuse revokes chain | Y | Y | Y | Y
Tenant isolation | Tests; live NOT VERIFIED | Critical if broken | 404 non-disclosure | Y tests | Condition | Condition | Retest
RBAC | In code + tests | High | editor not analyst | Y | Y | Y | Retest
Login rate limit | Fail-open on Redis error | Medium | rate_limit.py | N | N | N | Harden
Reset token hashed | In code | High | password reset tokens | Y | Y | Y | Y
Invitation token hashed | In code | High | token_hash stored | Y | Y | Y | Y
Connection secret encryption | In code; dummy key in Compose | Critical if dummy in prod | CONNECTION_ENCRYPTION_KEY | N | Y defaults | Y | Y
Malware scan | ClamAV API; workers noop Compose | High | FILE_MALWARE_SCANNER | N | Y copy | Y | Y
CORS wildcard forbidden in prod | In code | High | Settings validator | Y | Y | Y | Y
MFA / SSO | Absent | Medium enterprise | Not implemented | N | N | Disclose | Disclose
Live WAF/TLS | NOT VERIFIED | High | No public env | N | Condition | Y | Y

## Infrastructure
Infrastructure
DEFINITION READY — LIVE ENVIRONMENT NOT VERIFIED
Component | In repo | Live | Classification | Gap | Next action | Phase
Docker Compose local | Y | N this audit | LOCAL ONLY | Daemon down 23 Aug | docker compose up | P0
API Dockerfile | Y | N | Needs HEALTHCHECK | Single-stage | Add HEALTHCHECK; scan | P3
Web Dockerfile | Y | N | Already ready for first deploy | Multi-stage nginx | Build from tag | P3
Terraform ECS/RDS/Redis/EFS/ALB/WAF/Backup/SES | Y | N | Definition ready | Never applied | terraform apply staging | P3
Route53 / Cloudflare | Placeholder example.com | N | ABSENT | No zone | Cloudflare DNS | P1
Resend | N | N | ABSENT | Recommended bridge | SMTP env | P1
SES | email.tf | N | Definition ready | eu-central-1 | Apply after AWS | P3
Sentry | N | N | ABSENT | No DSN | Add SDK | P3
Uptime | N | N | ABSENT | — | UptimeRobot | P3
S3 app storage | N | N | ABSENT | Local+EFS V1 | Defer adapter | P5
CI quality-gate | Y | NOT VERIFIED run | EXISTS | Dirty yaml in tree | Run on tag | P2
CD deploy-certified-release | Y | NOT VERIFIED | EXISTS | OIDC envs needed | One staging deploy | P3

## Operations
Operations
Paper vs proven
Procedure | Doc exists? | Executed? | Status | Gap
Local compose up | Y | N this audit | NOT VERIFIED | Docker down
Create org/workspace/admin | Partial | Operator path in code | Manual OK for pilot | No invite email
User invitation | Config only | N | BROKEN as product | FIND-003
Upgrade / migrate | Alembic + ECS task in IaC | N live | Definition | Never run in AWS
Backup | AWS Backup tf + local drill | Local only | PARTIAL | FIND-013
Restore | LOCAL_RESTORE_DRILL PASS | AWS N | PARTIAL | Must restore RDS
Restart workers | Compose restart | N live | PARTIAL | Need prod evidence
Scheduler troubleshooting | Code SKIP LOCKED | N live | PARTIAL | FIND-015
Email troubleshooting | File outbox | N live | ABSENT SMTP | FIND-002
Tenant offboarding | N proven | N | ABSENT | Write SQL/EFS delete
Incident handling | N | N | Founder only | Name phone + Sentry
On-call | N | N | ABSENT | Founder 5x8 honest

## Commercial Gaps
Commercial gaps
Needed-for is the earliest commercial gate
Material | Exists? | Needed for | Notes
Honest feature list | Partial (this audit) | Demo | Use sales-safe matrix
Supported connectors | In catalog.py | Demo | Export Available vs beta vs planned
Product boundaries PDF | N | Demo | No AI/Reports/Automation
Architecture one-pager | Partial docs | Pilot | Must say Bahrain + unapplied
Security overview | N customer-facing | Pilot | Draft from this audit
Deployment model | IaC docs | Before contract | Not live
Trial process | N | Pilot | Founder-operated
Support process | N | Pilot | Inbox + hours
Pricing | N | Before contract | ABSENT
SLA | N | Later | Do not invent 99.9%
Data retention | Partial config TTLs | Before production | Need customer policy
Backup/RPO/RTO | Targets only | Before production | Not contractual
Privacy policy | N | Before contract | ABSENT
Terms | N | Before contract | ABSENT
DPA | N | Before contract | ABSENT
PDPL addendum | N | Before contract | ABSENT
Offboarding | N | Before production | ABSENT

## SaaS Productization
SaaS productization
Gap between a good app and a real product
Capability | App ready? | Productized? | Blocker class | Next
Multi-tenant app | Y | N hosted | Production | Apply AWS
Public URL | N | N | Trial public | Domain+Cloudflare
TLS | Code ready | N | Production | ACM/Cloudflare
Password reset email | Y code | N | Pilot/Prod | Resend
Invite email | N | N | Sale self-serve | Build+Resend
Durable files | Local driver | N live | Production | EFS
Managed DB | Y local PG | N | Production | RDS
Managed Redis | Y local | N | Production | ElastiCache
Secrets | Y validators | N | Production | SM
Backups | Local drill | N AWS | Production | Restore test
Monitoring | JSON+metrics code | N | Production | Sentry+uptime
Staging | N | N | Production | Second stack
CD | Workflow file | NOT VERIFIED | Production | OIDC deploy
Versioning | 0.1.0 | N | Sale | Tag SHA
Legal | N | N | Sale | Counsel
Billing | Gated mock | N | Later | Defer
Self-serve signup | N | N | Later | Defer after invites

## Sales Safe Matrix
Sales-safe feature matrix
If it is not Y under Sell, do not quote it as GA
Capability | Demo? | Trial? | Can sell? | Production? | Limitation
Authentication | Y | Y | Y | Condition | Hosted HTTPS
Password reset | Y | Condition | Condition | N | Until SMTP live
User invitations | Operator | Operator | N | N | No email/UI
Organizations / workspaces | Y | Y | Y | Y | Operator create
RBAC owner/admin/editor/viewer | Y | Y | Y | Y | No analyst role name
PostgreSQL connector | Y | Y | Y | Y | GA
CSV/XLSX upload | Y | Y | Y | Y | Size/row caps
Other catalog connectors | Careful | Beta only | N as GA | N | Honest catalog
Datasets | Y | Y | Y | Y | PG preview
Pipeline Studio | Y | Y | Y | Y | 100k rows
Data Quality | Y | Y | Y | Y | —
Semantic layer | Y | Y | Y | Y | PG only
Dashboards | Y | Y | Y | Y | —
Published viewer | Y | Y | Y | Y | —
PDF/PNG export | Y | Y | Y | Condition | Worker+storage
Scheduling | Y | Y | Y | Condition | Singleton soak
In-app notifications | Y | Y | Y | Y | Not email
Email alerts | N | N | N | N | Dashboard SMTP only when configured
Help | Y | Y | Y | Y | Static
Reports | N | N | N | N | Gated
AI Studio | N | N | N | N | Gated
Automation | N | N | N | N | Gated
Billing | N | N | N | N | Gated
Marketplace | N | N | N | N | Gated
SSO/MFA | N | N | N | N | Not V1
KSA in-country residency | N | N | N | N | Bahrain design

## Go-Live Requirements
Go-live requirements
All currently UNCHECKED
Category | Requirement | Testable check | Current
Domain | Owned domain | WHOIS/company | ABSENT
DNS | app/api/staging records | dig | ABSENT
TLS | HTTPS + redirect | curl -I | ABSENT
Application | Tagged SHA on version endpoint | GET /version | 0.1.0 / unpushed
Database | RDS + restore test | API on restored DB | Local drill only
Redis | Managed + documented fail mode | Stop Redis staging | Local only; fail-open
Workers | Healthy; scanner not noop | EICAR | Compose noop worker
Scheduler | Singleton 24h | One fire | NOT VERIFIED
Storage | Durable EFS | Task replace | Local volume
Email | SMTP + 3 mailboxes | Reset+invite | File/disabled
Secrets | No dummy keys | Task def audit | Compose dummies
Monitoring | Sentry+uptime | Force 500 | ABSENT
Backups | PITR + drill | Ticket dated | AWS NOT EXECUTED
Security | Live tenant isolation | Script org A vs B | Tests only
Onboarding | Admin invite or operator + UAT mail | Customer logs in | Operator only
Docs | Runbook used by 2nd engineer | Restart worker | Paper
Support | Named human + hours | Dummy P2 | Founder informal
Commercial | SOW + DPA | Signed | ABSENT
Compliance | Residency letter | Signed | ABSENT

## Deferred Enhancements
Deferred
Do not do these before first production customer unless a contract pays
Item | Why wait | Revisit
Kubernetes | Five processes; ECS is enough | Never unless required
SOC 2 / ISO 27001 | No live prod yet | After 3–5 customers
Cloudflare Enterprise / Bot Mgmt | Free DNS+WAF enough | If attacked / questionnaire
Native S3 storage adapter | EFS POSIX matches local driver | P5
Remaining ~90 connectors | Honesty > catalog vanity | Customer demand
AI Studio / Reports / Automation / Marketplace / Billing | Gated by design | Product roadmap
Self-serve signup + Stripe | No PMF proof | After invites work
Multi-region active-active | Cost/complexity | After SLA sold
Per-customer AWS accounts | Ops burden | If contract requires
SSO/SAML/MFA | V1 password+RBAC | First enterprise RFP that requires it
OpenTelemetry mesh / Grafana | Sentry+CW enough | When many services
KSA in-country region | Needs legal+rebuild | If deal requires

## Scorecard
Scorecard
Not a blind average — commercial/deploy/ops weighted in the 51 overall
Area | Score
Product Completeness | 76
Functional Reliability | 70
Data Integrity | 73
UX / Customer Experience | 68
Security | 74
Multi-Tenancy | 84
Performance | 55
Deployment Readiness | 26
Operational Readiness | 38
Documentation | 70
Commercial Readiness | 20
Enterprise Readiness | 44
SaaS Productization | 31
Observability | 34
Backup / DR Readiness | 28
Overall | 51